2026 年

活　动　方　案

校园自我保护与基础防身术工作坊

主办单位：中国文化教学中心自我管理课程组、SafeSpace 安心岛

联合社团：综合格斗社

2026年10月

目　录

一、活动主题	3

二、活动背景	3

三、活动目的	3

四、活动时间与地点	3

五、活动流程	4

（一）前期准备阶段	4

（二）活动进行阶段	4

（三）后期总结阶段	5

六、前期准备	5

七、人员分工	6

八、资金预算	6

九、应急预案	7

十、附件	7

一、活动主题

中国文化教学中心自我管理课程组、SafeSpace 安心岛主办，综合格斗社联合开展——“校园自我保护与基础防身术工作坊”

二、活动背景

本活动由中国文化教学中心自我管理课程组与 SafeSpace 安心岛共同主办，综合格斗社联合开展，面向全校学生提供零基础友好的自我保护工作坊，将安全意识教育与规范、低强度的基础防身训练结合。活动强调“避险优先、脱离优先”，帮助参与者建立更现实、可执行的风险判断与行动选择。

根据与教练的最新沟通，90分钟核心课程将保证约60分钟靶具实操。教学先讲解撤离优先、最低限度防护与反击边界，再以图示和演示说明人体易受伤区域的风险，随后在拳靶/脚靶上进行手部、肘部与腿部基础动作练习。所有实操均以安全、可控、可随时停止为前提，不以参与者身体薄弱部位作为直接击打目标。

三、活动目的

1. 安全教育目标：强化风险识别、边界表达、撤离与求助意识，使参与者理解“能避则避、能跑则跑”，自我保护的首要目标是降低风险并尽快脱离危险。

2. 技能体验目标：在教练指导下体验基础手部、肘部和腿部防身动作及靶具训练，学习控制距离、稳定动作与安全停止机制，不追求对抗强度或“实战胜负”。

3. 校园支持目标：通过中国文化教学中心自我管理课程组、SafeSpace 安心岛与综合格斗社协作，提升同学的自我保护与同伴支持意识，倡导尊重、自愿参与、包容和不责怪受害者的校园安全文化。

四、活动时间与地点

活动时间：2026年10月13日（周二，Week 5），核心课程90分钟；具体开始时间待最终确认。

活动地点：体育馆302搏击室（场地较大，自带软垫，适合约30人分组练习）。
预计规模：约30人，面向全校学生，零基础可参加；建议满额后进入候补名单。

五、活动流程

（一）前期准备阶段

1. 物资准备：活动前3天完成物资核对。场地自带软垫；拳套和拳靶由综合格斗社提供。SafeSpace准备基础急救包、冰袋/一次性冷敷用品、消毒湿巾/纸巾、饮用水、签到二维码/名单、参与者须知和反馈二维码。

2. 场地与安全检查：活动当天提前45-60分钟到体育馆302搏击室，检查软垫、防滑情况、训练间距、拳靶/脚靶、现场动线与急救物资；明确休息区和不参与实操的旁听区域。

3. 人员与参与者确认：活动前3天确认教练、综合格斗社工作人员及SafeSpace各部门现场人员；完成正式名单和候补名单，并向参与者发送时间、地点、运动服装建议、身体情况提醒、双人练习同意与随时退出机制。

（二）活动进行阶段

1. 签到与入场：活动开始前20分钟开放签到。组织部工作人员核对名单并引导入场；参与者可选择旁听或参加实操，不愿出镜者可提前向工作人员说明。

2. 开场与安全说明：活动负责人/主持人介绍中国文化教学中心自我管理课程组、SafeSpace 安心岛、综合格斗社及活动目标；说明停止口令、退出机制、双人配合规则和“自我保护优先于对抗”的原则。

3. 教练说明：教练强调“避险和撤离优先”；仅在无法安全撤离时讨论最低限度、以创造脱离机会为目的的防护与反击边界。人体易受伤区域仅作风险识别与安全教育，不进行人体直接击打训练。

4. 90分钟核心课程：
0-10分钟：避险优先、安全原则与训练规则；
10-30分钟：风险识别、人体易受伤区域图示/演示及防护边界；
30-90分钟：靶具实操。以手部动作、抱头撞肘、正蹬为主要练习内容；弹踢视教练现场判断作为可选演示或低强度靶练。所有实操均使用拳靶/脚靶等器材，控制力度，不安排全接触对抗。

5. 实操组织：由教练和综合格斗社工作人员负责动作示范、分组、持靶方式、强度控制与技术安全；参与者不得自行加力、加速或增加难度，任何人喊停均应立即停止。

6. 结束与反馈：核心课程结束后安排简短Q&A和反馈二维码；提醒参与者课程不等同于专业格斗训练，也不能保证真实风险场景中避免伤害。合影自愿参加，随后清点器材并恢复场地。

（三）后期总结阶段

1. 活动记录与宣传：活动结束后24小时内整理签到、反馈、照片和短视频素材；经宣传部审核后用于社团群、公众号或后续活动复盘，不公开不愿出镜参与者的影像。

2. 复盘与归档：活动负责人汇总组织部、活动部、宣传部、综合格斗社与教练反馈，形成活动复盘；组织部财务负责人按学校要求整理预算、发票、支付截图和相关财务记录。

六、前期准备

1. 场地与器材：确认体育馆302搏击室预定；场地自带软垫。综合格斗社提供拳套、拳靶/脚靶等训练器材；活动前检查器材完整性、场地防滑和训练间距。

2. 宣传与报名：通过SafeSpace公众号、综合格斗社社群、学校公邮、微信群/朋友圈及必要的线下海报发布活动信息。报名上限约30人并设置少量候补，活动前3-5天进行二次确认。宣传内容强调“零基础、专业教练、低强度靶练、自我保护意识”，避免夸张或性别刻板表达。

3. 安全与资料准备：通过问卷星设置健康状况确认环节，提醒参与者本次活动包含一定强度的搏击及防身术实操。参与者需确认自身不存在高血压、心脏病、心脑血管疾病或其他不适宜参加剧烈运动的健康状况。如存在相关疾病、身体不适或其他潜在风险，建议不参与实操环节。

报名/群通知中写明运动服装建议、身体不适者可旁听、双人练习需双方同意、可随时退出、禁止恶意加力和擅自练习未教学动作；准备参与者须知、风险评估、应急联系人和摄影不出镜机制。

七、人员分工

| 工作项目 | 人员名单 | 人数 |
| --- | --- | --- |
| 总负责人 / Leader | 聂靖霖 | 1 |
| 教学与技术安全 | 教练 ，荆冠宁 | 2 |
| 活动流程 / 主持 | 聂靖霖 | 1 |
| 场地 / 报名 / 签到 / 后勤 | 应佳卉 | 1 |
| 财务 / 报销 | 张琰 | 1 |
| 宣传 / 摄影 / 后宣 | 吴允儿 | 1 |
| 外部沟通 / 合作对接 | 刘乙可 | 1 |
| 现场秩序 / 应急协同 | 聂靖霖，荆冠宁 | 2 |

注：本活动采用“活动负责人 → 各部门部长 → 管理层 → 按需要安排社员”的执行方式。活动负责人负责跨部门统筹和最终决策；部长负责本部门分工、进度检查与成果验收；管理层推进具体模块；普通社员承担签到、引导、摄影、物资等可拆分执行任务。财务事项由组织部财务负责人专项处理。

八、资金预算

经费审批说明：本活动经费需通过中国文化教学中心自我管理课程组所在部门的经费审批流程。所有费用以部门最终审批结果为准，审批通过后方可进行采购或支付，并按要求保留预算、发票、支付凭证等材料。

| 项目 | 金额（元） | 备注 |
| --- | --- | --- |
| 安全/消耗物资、基础补给及机动费用 | 100-200 | 冷敷/消毒用品、饮水及审批范围内必要支出。 |
| 宣传/打印 | 0-50 | 优先线上宣传；线下海报按需申请。 |
| 训练器材 | 0 | 软垫由场地提供；拳套、拳靶/脚靶由综合格斗社提供。 |
| 合计 | 约150-250 |  |

九、应急预案

1. 一般不适或轻微受伤：立即停止该参与者练习，转移至安全区域进行基础处理与观察；必要时使用冷敷用品，并联系校内医疗资源。

2. 较严重受伤或突发身体不适：立即停止相关区域训练、保持现场秩序，由指定负责人联系急救/校内安保并按学校流程上报；保留必要事件记录。

3. 场地、器材或训练秩序问题：如发现软垫移位、地面湿滑、器材损坏或参与者擅自加力，立即暂停相关练习；问题无法及时排除时取消该环节。报名人数超过安全容量时停止新增入场。

4. 教学与人员突发情况：教练临时无法到场时不自行替换高风险实操内容，由活动负责人和综合格斗社共同决定延期、调整为安全教育/演示或取消；现场出现情绪不适或冲突时优先停止练习、隔离风险并沟通处理。

十、附件

1. 活动安全协议 / 参与者须知

2. 财务预算与报销材料

3. 体育馆302搏击室场地信息 / 场地照片

4. 风险评估表

5. 教学流程表及教练/综合格斗社教学人员信息

| 社团名称 | 节目名称 | 节目类型 | 人数 | 时长 |
| --- | --- | --- | --- | --- |
| 综合格斗社 | 避险优先与安全规则 | 讲解 | 约30 | 10分钟 |
| 综合格斗社 | 风险识别与人体易受伤区域 | 讲解/演示 | 约30 | 20分钟 |
| 综合格斗社 | 手部防身动作靶练 | 实操 | 约30 | 15分钟 |
| 综合格斗社 | 抱头撞肘靶练 | 实操 | 约30 | 15分钟 |
| 综合格斗社 | 正蹬靶练 | 实操 | 约30 | 15分钟 |
| 综合格斗社 | 综合靶练；弹踢按教练判断可选 | 实操 | 约30 | 15分钟 |
| SafeSpace × 综合格斗社 | Q&A / 反馈 / 自愿合影 | 互动 | 约30 | 课后5-10分钟 |

2026

ACTIVITY PROPOSAL

Campus Self-Protection and Basic Self-Defence Workshop

Organisers: Self-Management Course Group, Chinese Culture Teaching Centre & SafeSpace

Partner Society: 综合格斗社

October 2026

Table of Contents

1. Theme	11

2. Background	11

3. Purpose	11

4. Time & Venue	11

5. Process	12

5.1 Preparation Stage	12

5.2 Execution Stage	12

5.3 Follow-up Stage	13

6. Preparation	13

7. Personnel Division of Labour	14

8. Budget	14

9. Emergency Plan	15

10. Attachments	15

1. Theme

Organised by the Self-Management Course Group, Chinese Culture Teaching Centre and SafeSpace, in collaboration with 综合格斗社 — “Campus Self-Protection and Basic Self-Defence Workshop”

2. Background

This activity is jointly organised by the Self-Management Course Group, Chinese Culture Teaching Centre (中国文化教学中心自我管理课程组) and SafeSpace, in collaboration with 综合格斗社. It offers XJTLU students a beginner-friendly workshop combining safety education with structured, low-intensity self-defence training. The core message is “avoid and leave first”: self-protection should reduce risk and create a safe opportunity to disengage.

Based on the latest discussion with the coach, the 90-minute core session will include approximately 60 minutes of supervised pad-based practice. The coach will first explain escape-first principles, proportionate defensive boundaries and vulnerability awareness, followed by controlled hand, elbow and kicking drills using pads. No participant will be used as a direct striking target for vulnerable body areas.

3. Purpose

1. Safety education goal: strengthen risk recognition, boundary setting, disengagement and help-seeking awareness, and reinforce that avoiding danger and leaving safely take priority over confrontation.

2. Practical experience goal: allow beginners to experience basic hand, elbow and kicking movements through supervised pad work, with emphasis on control, distance, consent and the stop mechanism rather than intensity or winning.

3. Campus community goal: promote peer support, respect, voluntary participation, inclusion and a non-victim-blaming approach through collaboration among the Self-Management Course Group, Chinese Culture Teaching Centre, SafeSpace and 综合格斗社.

4. Time & Venue

Time: 13 October 2026 (Tuesday302, Week 5); 90-minute core session. Exact start time to be confirmed.

Venue: Sports Centre Room  Combat Training Room. The room is spacious and equipped with mats, suitable for approximately 30 participants.
Expected participants: approximately 30 XJTLU students; beginners are welcome.

5. Process

5.1 Preparation Stage

1. Materials: Complete the final material check three days before the event. Mats are available at the venue; gloves and striking pads will be provided by 综合格斗社. SafeSpace will prepare a first-aid kit, cold packs, disinfecting wipes/tissues, drinking water, sign-in materials, participant guidelines and a feedback QR code.

2. Venue and safety check: Arrive 45-60 minutes early to inspect the mats, floor condition, training distance, pads, participant flow and first-aid supplies, and designate a rest/observation area for participants who do not take part in practice.

3. Personnel and participant confirmation: Three days before the event, confirm the coach, 综合格斗社 supporting staff and SafeSpace staff. Finalise the participant and waiting lists and send clothing, health, consent, stop-mechanism and opt-out reminders.

5.2 Execution Stage

1. Sign-in and entry: Open sign-in 20 minutes before the session. Organisation staff will check the list and guide participants into the venue. Participants may observe only, and anyone who does not wish to be photographed may inform staff in advance.

2. Opening and safety briefing: The activity leader/host introduces the Self-Management Course Group, Chinese Culture Teaching Centre, SafeSpace, 综合格斗社 and the purpose of the workshop, then explains the stop command, opt-out mechanism, partner-practice rules and the principle that self-protection takes priority over confrontation.

3. Coach briefing: The coach reinforces escape-first decision-making. Only when safe disengagement is not possible will the session discuss minimum, proportionate protective responses intended to create an opportunity to leave. Vulnerable body areas are covered for awareness only and are not used as direct-contact practice targets.

4. 90-minute core session: 
0-10 min: escape-first principles, safety rules and training boundaries;
10-30 min: risk recognition, vulnerability awareness and demonstration of protective boundaries;
30-90 min: controlled pad-based practice. Main content includes hand techniques, a guarded elbow movement and front-kick practice; an additional kicking movement may be demonstrated or practised on pads only at the coach’s discretion. No full-contact sparring is included.

5. Practical organisation: The coach and 综合格斗社 staff supervise demonstrations, grouping, pad holding, intensity control and technical safety. Participants must not add force, speed or difficulty on their own; any stop call must be respected immediately.

6. Closing: After the core session, allow a short Q&A and collect feedback. Remind participants that the workshop is not a substitute for professional training and cannot guarantee safety in real-world incidents. Group photos are voluntary, followed by equipment count and venue restoration.

5.3 Follow-up Stage

1. Records and publicity: Within 24 hours, organise attendance data, feedback, photos and short-video material. Publicity content should be reviewed before release, and images of participants who opted out of photography must not be published.

2. Review and filing: The activity leader consolidates feedback from SafeSpace departments, 综合格斗社 and the coach. The Organisation Department finance lead keeps the approved budget, invoices, payment screenshots and other required financial records.

6. Preparation

1. Venue and equipment: Confirm Sports Centre Room 302. The venue provides mats; 综合格斗社 provides gloves and striking pads. Check equipment condition, floor safety and practice spacing before the event.

2. Promotion and registration: Promote through the SafeSpace official account, 综合格斗社 channels, university email, WeChat groups/Moments and posters if needed. Cap registration at around 30 with a small waiting list and reconfirm attendance 3-5 days before the event.

3. Safety information: A health screening section will be included in the Wenjuanxing registration form to inform participants that the activity involves moderately intensive boxing and self-defense practice. Participants will be required to confirm that they do not have high blood pressure, heart disease, cardiovascular or cerebrovascular conditions, or any other health conditions that may make strenuous physical activity unsuitable. Participants with relevant medical conditions, physical discomfort, or other potential health risks will be advised not to take part in the practical training sessions.

The registration form/group notice should state clothing guidance, health reminders, consent for partner practice, the right to observe or withdraw at any time, prohibition of unauthorised techniques or excessive force, risk-assessment information and the photography opt-out mechanism.

7. Personnel Division of Labour

| Work Item | Members | No. |
| --- | --- | --- |
| Overall coordinator / Leader | Jinglin Nie | 1 |
| Teaching & technical safety | Yong.Fang Guanning.Jing | 2 |
| Programme / hosting | Jinglin.Nie | 1 |
| Venue / registration / logistics | Jiahui.Ying | 1 |
| Finance / reimbursement | Yan.Zhang | 1 |
| Publicity / photography / follow-up | Yuner.Wu | 1 |
| External liaison | Yike.Liu | 1 |
| Order / emergency coordination | Jinglin.Nie Guanning.Jing | 2 |

Note: the event follows the chain “Activity Leader → Department Heads → Management Members → Members assigned as needed”. The activity leader handles cross-department coordination and final decisions; department heads allocate and review work; management members drive specific modules; general members take on clearly scoped execution tasks. Finance is handled by the designated Organisation Department finance lead.

8. Budget

Funding approval note: The activity budget must follow the departmental funding approval process through the Self-Management Course Group, Chinese Culture Teaching Centre. All expenditure is subject to final departmental approval; purchases or payments may only be made after approval, with required budget, invoice and payment records retained.

| Item | Amount (RMB) | Note |
| --- | --- | --- |
| Safety consumables, basic refreshments and contingency | 100-200 | Cold packs, disinfecting supplies, water and necessary approved expenses. |
| Publicity / printing | 0-50 | Online publicity preferred; print only if needed. |
| Training equipment | 0 | Venue mats; gloves/pads provided by 综合格斗社. |
| Total | Approx. 150-250 |  |

9. Emergency Plan

1. Minor discomfort or injury: stop the participant’s practice immediately, move them to a safe area, provide basic first aid/observation and use a cold pack if appropriate; contact campus medical support if needed.

2. Serious injury or acute illness: stop the relevant training area, maintain order, contact emergency/campus security services through the designated person and report the incident according to university procedures.

3. Venue, equipment or unsafe practice: pause the relevant drill if mats shift, the floor becomes slippery, equipment is damaged or participants use excessive force. Cancel the drill if the risk cannot be removed promptly. Stop new entry if capacity becomes unsafe.

4. Coach/personnel contingency: if the coach cannot attend, do not replace the practical content with unapproved high-risk drills. The activity leader and 综合格斗社 will decide whether to postpone, convert to a safe educational/demonstration format, or cancel. Emotional discomfort or conflict will be handled by stopping practice and separating the risk first.

10. Attachments

1. Activity Safety Agreement / Participant Guidelines

2. Budget and Financial Records

3. Sports Centre Room 302 Venue Information / Photos

4. Risk Assessment

5. Training Schedule and Coach / 综合格斗社 Teaching Staff Information

| Society | Item | Type | No. | Duration |
| --- | --- | --- | --- | --- |
| 综合格斗社 | Escape-first principles & safety rules | Briefing | Approx. 30 | 10 min |
| 综合格斗社 | Risk recognition & vulnerability awareness | Briefing / Demo | Approx. 30 | 20 min |
| 综合格斗社 | Hand-technique pad drill | Practice | Approx. 30 | 15 min |
| 综合格斗社 | Guarded elbow pad drill | Practice | Approx. 30 | 15 min |
| 综合格斗社 | Front-kick pad drill | Practice | Approx. 30 | 15 min |
| 综合格斗社 | Integrated pad drill; optional additional kick | Practice | Approx. 30 | 15 min |
| SafeSpace × 综合格斗社 | Q&A / feedback / optional group photo | Interaction | Approx. 30 | 5-10 min after class |